## Test summary report
Tester | Mai Đăng Khánh, Hồ Nguyễn Huy Hoàng
Date | 2021-01-01
ID | Feature Name | Description | Number of Test case | Number of Pass | Number of Test fail
UC01 | Login as admin | Login as the manager of the cosmetic shop | 7 | 6 | 1 | Duplicated
UC02 | Login as customer | Login as the custom of the cosmetic shop | 7 | 6 | 1
UC03 | Register as admin | Register a admin account | 12 | 8 | 4 | Duplicated
UC04 | Register as customer | Register a customer account | 12 | 8 | 4
UC05 | Make purchase | Purchase all item in cart | 12 | 12 | 0
UC06 | Search product | Search product name or information in search bar | 8 | 5 | 3
UC07 | Browse product | View product summary and product detail | 10 | 7 | 3
UC08 | View cart | View all item in currently in cart | 12 | 12 | 0
UC09 | Edit product in cart | Change the attribute of a product currently in cart | 9 | 9 | 0
UC10 | Remove product from cart | Remove product in cart | 5 | 5 | 0
UC11 | Add product to cart | Add the viewing product to cart | 6 | 6 | 0
UC13 | Add new product | Admin add a new product to shop | 16 | 15 | 1
UC14 | Edit product | Admin edit the information of a product in shop | 20 | 11 | 9
UC15 | Delete product | Admin delete a product in shop | 5 | 2 | 3
UC16 | Edit profile as admin | Change information about admin user | 12 | 6 | 6 | Duplicated
UC17 | Edit profile as customer | Change information about customer | 13 | 7 | 6
UC20 | View shopping history | View all item purchased | 4 | 2 | 2
UC21 | Add comment | Comment about a product in produt detail | 12 | 9 | 3
UC23 | Change password as admin | Change password of admin account | 8 | 7 | 1 | Duplicated
UC24 | Change password as customer | Change password of customer account | 8 | 7 | 1
UC25 | Website navigation | Navigate the website from homepage | 13 | 13 | 0
UC26 | Order management | Choose and delete order | 4 | 0 | 4
UC27 | User management | Add, reset or remove user account | 7 | 2 | 5
|  | Total | 222 | 165 | 57

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Login with Special characters in User name as Admin | System allows user to enter special character for user name | UC001 | Medium | Mai Đăng Khánh | 2020-12-20 | Closed
B002 | Register with user name contain special character | System allows user to enter special character for user name while regiseter | UC003 | Medium | Mai Đăng Khánh | 2020-12-20 | Closed
B003 | Register with password contain space character | System allows user to enter space character for password while register | UC003 | Medium | Mai Đăng Khánh | 2020-12-20 | Closed
B004 | Register with fullname contain special character | System allows user to enter space character for password while register | UC003 | Medium | Mai Đăng Khánh | 2020-12-20 | Closed
B005 | Register with blank fullname | System allows user to not enter fullname while register | UC003 | High | Mai Đăng Khánh | 2020-12-20 | Closed
B006 | Search by category name | System does not support search product by category name | UC006 | Low | Mai Đăng Khánh | 2020-12-20 | Open
B007 | Search by exact price | System does not support search product by their price name | UC006 | Low | Mai Đăng Khánh | 2020-12-20 | Open
B008 | Search by price range | System does not support search product belong to specify price range name | UC006 | Low | Mai Đăng Khánh | 2020-12-20 | Open
B009 | Add new valid product | Cannot add new porduct to store | UC013 | High | Hồ Nguyễn Huy Hoàng | 2021-01-01 | Open | Function is not implemented
B010 | Edit product with Product name contain special character | System accept special character for product name when edit, display edit success | UC014 | Medium | Hồ Nguyễn Huy Hoàng | 2020-12-26 | Open
B011 | Edit product with stock contain special character | System accept special character for stock number when edit, display edit success | UC014 | Medium | Hồ Nguyễn Huy Hoàng | 2020-12-26 | Open
B012 | Edit product with negative stock number | System accept negative number for stock when edit, display edit success | UC014 | Medium | Hồ Nguyễn Huy Hoàng | 2020-12-26 | Open
B013 | Price contain special character | System accept special character for price when edit, display edit success | UC014 | Medium | Hồ Nguyễn Huy Hoàng | 2020-12-26 | Open
B014 | Price negative number | System accept negative for price when edit, display edit success | UC014 | Medium | Hồ Nguyễn Huy Hoàng | 2020-12-26 | Open
B015 | category contain special character | System accept special character for category when edit, display edit success | UC014 | Medium | Hồ Nguyễn Huy Hoàng | 2020-12-26 | Open
B016 | Product category not exist | System accept non-existed category for category when edit, redirect to new page with error message | UC014 | Medium | Hồ Nguyễn Huy Hoàng | 2020-12-26 | Open
B017 | Invalid big image file extension | System accept any type of file, not just image, display edit success | UC014 | Medium | Hồ Nguyễn Huy Hoàng | 2020-12-26 | Open
B018 | Invalid small image file extension | System accept any type of file, not just image, display edit success | UC014 | Medium | Hồ Nguyễn Huy Hoàng | 2020-12-26 | Open
B019 | delete by non existing id | Even product is not exist, display message success | UC015 | High | Hồ Nguyễn Huy Hoàng | 2020-12-27 | Open
B020 | delete by id contain special character | Redirect to new page with non-style database error | UC015 | High | Hồ Nguyễn Huy Hoàng | 2020-12-27 | Open | Function is not implemented
B021 | delete by id as character | Enter character as product id, redirect to new page with non-style database error | UC015 | High | Hồ Nguyễn Huy Hoàng | 2020-12-27 | Open | Function is not implemented
B022 | Edit profile Fullname contain special character | Enter special character for fullname when edit profile, system accept the special charater for fullname | UC017 | Medium | Hồ Nguyễn Huy Hoàng | 2021-01-01 | Open
B023 | Edit profile Address contains special characters | Enter special character for address when edit profile, system accept the special charater for address | UC017 | Medium | Hồ Nguyễn Huy Hoàng | 2021-01-01 | Open
B024 | Switch to tab Order history | While edit profile, switch tab should discard the change or at least display message that there are unsave changes. However, the changes are not discard | UC017 | Low | Hồ Nguyễn Huy Hoàng | 2021-01-01 | Open
B025 | Switch to tab Address | While edit profile, switch tab should discard the change or at least display message that there are unsave changes. However, the changes are not discard | UC017 | Low | Hồ Nguyễn Huy Hoàng | 2021-01-01 | Open
B026 | Switch to tab Security | While edit profile, switch tab should discard the change or at least display message that there are unsave changes. However, the changes are not discard | UC017 | Low | Hồ Nguyễn Huy Hoàng | 2021-01-01 | Open
B027 | Switch to tab Order management | While edit profile, switch tab should discard the change or at least display message that there are unsave changes. However, the changes are not discard | UC017 | Low | Hồ Nguyễn Huy Hoàng | 2021-01-01 | Open
B028 | View order date | The displayed date time format should be the simple format, but system display the long date time formate | UC020 | Low | Mai Đăng Khánh | 2020-12-23 | Open
B029 | View receive date | The displayed date time format should be the simple format, but system display the long date time formate | UC020 | Low | Mai Đăng Khánh | 2020-12-23 | Open
B030 | Long comment (>1000 character) | Can not have a too long comment, when submit nothing happen | UC021 | Medium | Mai Đăng Khánh | 2020-12-22 | Open | There seem to be a limit to the length of comment but is not specified how long. Testing indicate around (100,1000) character
B031 | Long comment (>10000 characters) | Can not have a too long comment, when submit nothing happen | UC021 | Medium | Mai Đăng Khánh | 2020-12-22 | Open | There seem to be a limit to the length of comment but is not specified how long. Testing indicate around (100,1000) character
B032 | Comment without rating | Comment should always have rating for product, but we can submit comment without rating but nothing is displayed | UC021 | Medium | Mai Đăng Khánh | 2020-12-22 | Open
B033 | New and old passwords are the same | System do not detect that the old password and new password are the same | UC023 | Low | Mai Đăng Khánh | 2020-12-22 | Open
B034 | Order management | Choose order to remove but encounter error Request not found | UC026 | High | Mai Đăng Khánh | 2020-12-23 | Open | Function is not implemented
B035 | User management | Admin manage user account, add, reset password, remove account. When take any action, encounter error request not found | UC027 | High | Mai Đăng Khánh | 2020-12-30 | Open | Function is not implemented
B036
B037
B038
B039
B040
B041
B042
B043
B044
B045
B046
B047
B048
B049
B050
B051
B052
B053
B054
B055
B056
B057
Note on D1: Function ID of the function where the defect is found
Note on E1: High, Medium, or Low
Note on F1: Name of the tester who reports the defect
Note on H1: Open or Closed